## Sheet1
Action | Sub-project | Q1 18 |  |  | Q2 18
|  | Jan | Feb | Mar | Apr
Governance Structures | Accountability Structures
Governance Structures | DPO
Governance Structures | Supervisory Authority
Governance Structures | Decision re Establishment
Governance Structures | Engagement of senior stakeholders
Governance Structures | Identification of Joint Controllers
Inventory of Personal Data within the organisation | Initial DPEA for baseline
Inventory of Personal Data within the organisation | Data Quality Assessment
Inventory of Personal Data within the organisation | Destruction of obsolete, excessive data
Inventory of Personal Data within the organisation | Amnesty re legacy data
Inventory of Personal Data within the organisation | Round-up of devices, storage solutions
Inventory of Personal Data within the organisation | Introduction of Asset Register
Inventory of Personal Data within the organisation | Review of Starter/Leaver/Mover
Data Protection Officer | Nomination
Data Protection Officer | Definition of Role, Responsibilities
Data Protection Officer | Training, induction
Data Protection Officer | Stakeholder engagement
Suite of Privacy Policies | Prepare Suite of privacy policies
Suite of Privacy Policies | Privacy Policy
Suite of Privacy Policies | Privacy Statement
Suite of Privacy Policies | Data Security Policy
Suite of Privacy Policies | Data Retention Policy
Suite of Privacy Policies | Data Destruction Policy
Suite of Privacy Policies | Data Retention Schedule
Suite of Privacy Policies | Acceptable Use Policy
Suite of Privacy Policies | Breach Notification Policy
Suite of Privacy Policies | Starter/Leaver/Mover Policy
Suite of Privacy Policies | Subject Access Request Policy
Suite of Privacy Policies | CCTV Policy
Suite of Privacy Policies | Vendor Selection Policy
Suite of Privacy Policies
Suite of Privacy Policies
Suite of Privacy Policies
PIA Privacy by Design and Default | Procedure
PIA Privacy by Design and Default | Agree Methodology
Privacy awareness embedded in operations | Retention Policy and practices
Privacy awareness embedded in operations | Access controls
Privacy awareness embedded in operations | Authorisation levels
Privacy awareness embedded in operations | CCTV usage
Privacy awareness embedded in operations | Social Media usage
Privacy awareness embedded in operations | Pseudonymisation of data
Privacy awareness embedded in operations | Minimisation of processing
Privacy awareness embedded in operations | BYOD controls
Training and Awareness-raising | Public
Training and Awareness-raising | Staff
Training and Awareness-raising | Customers
Training and Awareness-raising | Offences, fines and penalties
Information Security Risk Management | Cyber Risk Assessment
Information Security Risk Management | Updates to software
Information Security Risk Management | Disaster Recovery
Information Security Risk Management | BCP Solution
Third-Party Risk Management | Inventory of third-party service providers
Third-Party Risk Management | Review of contract status
Third-Party Risk Management | Introduction of GDPR_compliant contract template
Third-Party Risk Management | Selection criteria for future engagements
Third-Party Risk Management | Audits / Due Diligence of current activities
New Operational Practices | Review, reassessment of Lawful Processing Conditions
New Operational Practices | Re-evaluation of consent already in place
New Operational Practices | Documentation of opt in, registration details
New Operational Practices | Identification of childrens' data
New Operational Practices | Consideration of Legitimate Interest
Review of Fair Processing Notices | Review narratives, ensure transparency, openness
Review of Fair Processing Notices | Re-consider status of mandatory fields
Capacity for meeting DS Rights within timeline | Portability
Capacity for meeting DS Rights within timeline | Right to be Forgotten
Capacity for meeting DS Rights within timeline | Rectification / Erasure
Capacity for meeting DS Rights within timeline | Automated Processing / Profiling
Capacity for meeting DS Rights within timeline | Restriction of Processing
Capacity for meeting DS Rights within timeline | Right of Access to data
Data Breach Management | Detection
Data Breach Management | Prevention
Data Breach Management | Investigation
Data Breach Management | Reporting template
Data Breach Management | Resolution
Data Breach Management | Prevention of Recurrence
Data Breach Management | Reporting to ODPC
Data Breach Management | Notification to Data Subjects
Overseas Transfer of data | Privacy Shield status of recipients
Overseas Transfer of data | Nominated Representative status
Overseas Transfer of data | Model Contracts
Overseas Transfer of data | Binding Corporate Rules
Overseas Transfer of data | Legal Obligations
Overseas Transfer of data | Appropriate Derogations
Compliance with Standards | Standards
Compliance with Standards | Certification
Compliance with Standards | Qualification
Compliance with Standards | Assessment of compliance